# Project Status Report

## Executive Summary

This report provides an overview of the ConstructionProjectA progress for Q1 2026. Overall the project is on track with minor delays in the electrical subsystem.

## Timeline Overview

### Phase 1: Foundation

The foundation work has been completed ahead of schedule. All concrete pours passed quality inspection on the first attempt.

### Phase 2: Structural Framework

Steel framework is 85% complete. Remaining work includes:

- North wing upper floor beams

- Elevator shaft reinforcement

- Roof truss installation

### Phase 3: Systems Installation

Planned systems include:

- Electrical wiring and panel installation

- HVAC ductwork and unit placement

- Plumbing rough-in and fixtures

- Fire suppression system

## Budget Summary

| Category | Budget | Actual | Variance |
| --- | --- | --- | --- |
| Foundation | €250,000 | €243,500 | -€6,500 |
| Structural | €890,000 | €912,000 | +€22,000 |
| Electrical | €340,000 | €185,000 | In Progress |
| HVAC | €275,000 | €45,000 | In Progress |
| Plumbing | €180,000 | €0 | Not Started |
| Total | €1,935,000 | €1,385,500 |  |

## Risk Assessment

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Material delivery delays | Medium | High | Pre-ordered steel for Phase 3 |
| Weather disruptions | Low | Medium | Indoor work scheduled for winter months |
| Subcontractor availability | High | Medium | Contracts signed with backup firms |
| Permit delays | Low | Low | All permits filed 60 days in advance |

## Key Decisions Required

The project steering committee needs to approve the revised electrical plan by March 15th to avoid schedule impact on Phase 3 systems installation.

## Next Steps

- Complete north wing beam installation by Feb 28

- Begin electrical rough-in on March 1

- Schedule HVAC contractor kickoff meeting

- Submit Phase 3 permit amendments

Report prepared by the Project Management Office — February 2026